## Slide 1: IS 430: Fundamentals of IT Project Management
WEEK ONE: january 4, 2016

## Slide 2: Agenda
Introduction
Syllabus
Chapter 1 – Overview
Chapter 2 – Project Mgmt Growth: Concepts and Definitions
Next Week

## Slide 3: Introduction
Kerry Good
  Director in the IT PMO – Manage project managers, ITSM (IT Service Management) Platform, IT Metrics
  Manage 9 different portfolios within the company
  7 years experience managing an IT PMO
  18 years experience in IT
  Roles ranging from BA, Developer, QA, to Project Manager
  Managed small to large projects in the past as well as programs
  Managed an application development team

## Slide 4: Introduction
Your turn
  Name
  Masters program
  Work experience in project management
  Plans after graduation
  What do you want to get out of this course?

## Slide 5: Syllabus
Instructor: Kerry Good
e-mail: kgood1@cdm.depaul.edu
Office Hours:
  Monday 5:00pm to 5:45pm in Lewis Hall 1107
  Monday 9:00pm to 9:45pm in Lewis Hall 1107
Phone: 708-557-8026

## Slide 6: Syllabus
Learning Outcomes:
Students will be able to:
  Explain and contrast the key dimensions of the Project Management Body of Knowledge (PMBOK) framework
  Understand the advantages and disadvantages of various approaches for incorporating project teams into organizational structures and be able to recommend optimal approaches for a variety of situations.
  Apply fundamental IT project planning techniques for scope, estimating, and scheduling
  Apply the techniques needed to assess and control a project budget.

## Slide 7: Syllabus
Learning Outcomes:
  Assess project progress using techniques such as earned value management.
  Analyze a project plan, or a description of a completed project, for best practices and lessons learned.
  Develop the ability to manage team communications, motivate team members, and deal with potentially harmful behavior within a team.
  Ability to develop a project charter.
  Discuss emerging trends and issues in IT project management

## Slide 8: Syllabus
Text Book:
Project Management: A Systems Approach to Planning, Scheduling, and Controling, 11th ed. Kerzner, John Wiley & Sons, 2013. ISBN: 978-1118022276
Software:
Many of the deliverables of project management can be produced using general-purpose tools such as Word, Excel, and PowerPoint. Some documents are best produced using a project scheduling tool:
Microsoft Project Professional 2013 or Microsoft Project Standard 2013
The software is available on the CDM lab machines or can be purchased here (http://offices.depaul.edu/is/services/Software/Pages/Software-for-Personal-Computers.aspx).

## Slide 9: Syllabus
Grading:
30% Quizzes / Homework – Due by 5:30pm on Mondays 30% Midterm Exam – Week 6
30% Final Case Study/Project – Due Week 11
10% Participation/attendance (discussion forum participation (online students)**)
**Online students earn participation credit by posting their insights, thoughts, concerns, etc. on the weekly discussion forum after reading the required assignments and watching the weekly lecture. Students should be conversing with one another to get credit. To get credit the postings must be made during the discussion forum’s open period. The quality of the weekly in-class and online discussions plays a large role in helping you understand your project management knowledge. To ensure a quality ongoing conversation, I have provided answers to some frequently asked questions.
9-10 Consistently asks good questions, makes valuable observations, and answers questions effectively
8-9 Frequent participant, but not all questions, answers, and observations are effective, or not consistently
  active
7-8 Participates infrequently, or questions/answers do not reflect adequate preparation, or late to class
6-7 Very rare participation, or questions/answers reflect little or no preparation, or very late to class
<6 Displays no sign of life, or absent for entire class

## Slide 10: Syllabus
Grading Scale:
98 - 100 A+ 92 - 97 A 90 - 91 A- 88 - 89 B+
82 - 87 B
80 - 81 B- 78 - 79 C+ 72 - 77 C
70 - 71 C- 68 - 69 D+
62 - 67 D 60 - 61 D- 0 - 59 F
Late assignments
Late assignments will be penalized unless prior arrangements have been made with the instructor. In general, you will lose 15% of the possible credit if less than 1 week late, 25% of the credit if 1-2 weeks late, 50% of the credit if 2-3 weeks late, and 100% of the credit if more than 3 weeks late or if turned in after the last class session. For the OL students, you must respond to a post within the timeframes specified in D2L; if you miss the time window, there will be nobody to participate with and it will be impossible for you to earn credit.

## Slide 11: Syllabus
Week | Date | Chapter: Topic | Assignment Due | Quiz Due
1 | 1/4/16 | Course Overview Chapter 1: Overview Chapter 2: PM Growth – Concepts and Definitions |  | 
2 | 1/11/16 | Chapter 3: Organizational Structures Chapter 4: Organizing and Staffing the Project Office and Team Chapter 5: Management Functions |  | Quiz 1
3 NO CLASS | 1/18/16 MLK Holiday | Chapter 6: Management of your Time and Stress Chapter 7: Conflicts | Assignment 1 | Quiz 2
4 | 1/25/16 | Chapter 8: Special Topics Chapter 9: The Variables for Success Chapter 10: Working with Executives |  | Quiz 3
5 | 2/1/16 | Chapter 11: Planning Chapter 12: Network Scheduling Techniques CDM LAB | Assignment 2 | Quiz 4
6 | 2/8/16 | Chapter 13: Project Graphics Mid Term Exam |  | 
7 | 2/15/16 | Chapter 14: Pricing and Estimating Chapter 15: Cost Control | Assignment 3 | Quiz 5

## Slide 12: Syllabus
Week | Date | Chapter: Topic | Assignment Due | Quiz Due
8 | 2/22/16 | Chapter 16: Trade-off Analysis in a Project Environment Chapter 17: Risk Management | Assignment 4 | Quiz 6
9 | 2/29/16 | Chapter 19: Contract Management Chapter 20: Quality Management Chapter 21: Modern Developments in Project Management | Assignment 5 | Quiz 7
10 | 3/7/16 | Chapter 22: The Business of Scope Changes Chapter 24: Managing Crisis Projects Chapter 25: Future of Project Management |  | 
11 | 3/14/16 | Final Project Due |  | 

## Slide 13: Syllabus
Attendance:
Attend each class and remain for the duration.
Coming 15 minutes late or leaving 15 minutes early constitutes an absence
The overall grade for participation drops one-third after any absence. Three absences for any reason, whether excused or not, may constitute failure for the course.
Class Discussion:
Participation measured in two ways.
  Encouraged to ask questions and offer comments relevant to the day’s topic.
  Students will be called upon by the instructor to offer comments related to the reading assignments.

## Slide 14: Syllabus
Attitude:
A professional and academic attitude is expected throughout the course.
Examples of non-academic or unprofessional attitude include but are not limited to:
  Talking to others when the instructor is speaking
  Mocking another’s opinion
  Cell phones ringing
  Emailing, texting or using the internet whether on a phone or computer.
If any issues arise, a student may be asked to leave the classroom. The instructor will work with the Dean of Students Office to navigate such student issues.
Cell Phones/On Call/Laptops:
If you bring a cell phone to class, it must be off or set to a silent mode.
Should you need to answer a call during class, students must leave the room in an undisruptive manner.
Laptops must also be closed during class unless we are using software on your laptop as part of the class instruction.

## Slide 15: Syllabus
Questions?

## Slide 16: Chapter 1
overview

## Slide 17: Learning Objectives
Understand the definition of project management
Discuss the benefits of project management
Explain responsibilities of the project manager

## Slide 18: Overview of Project Management
TIME
COST
PERFORMANCE/TECHNOLOGY
RESOURCES

## Slide 19: Project Characteristics
Have a specific objective (which may be unique or one-of-a-kind) to be completed within certain specifications
Have defined start and end dates
Have funding limits (if applicable)
Consume human and nonhuman resources (i.e., money, people, equipment)
Be multifunctional (cut across several functional lines)

## Slide 20: Project Management
Project Planning
  Definition of work requirements
  Definition of quantity and quality of work
  Definition of resources needed
Project monitoring
  Tracking progress
  Comparing actual outcome to predicted outcome
  Analyzing impact
  Making adjustments

## Slide 21
WHY USE PROJECT MANAGEMENT ?

## Slide 22: Maturity in Project Management
MATURITY IN PROJECT MANAGEMENT IS LIKE A THREE - LEGGED STOOL.
THE LEGS REPRESENT THE:
Project Manager
Line Manager(s)
Executive Management (i.e... Project Sponsor)
Maturity cannot exist without stability

## Slide 23: The Three-Legged Stool
Project
Manager
Line
Management
Management
Senior
(I.e. Sponsor)

## Slide 24: Top of The Three-Legged Stool
ORGANIZATIONAL
STRUCTURE
ORGANIZATIONAL
BEHAVIOR
TOOLS &
TECHNIQUES

## Slide 25
How important is Project Management training ?
Part-time Project Management - is it good or bad ?
Critical Questions

## Slide 26: Role Of The Project Manager
Negotiating Resources
Project Kick Off Meeting
Establishing The Project’s Policies and Procedures
Laying Out The Project Workflow And Plan
Establishing Performance Targets
Obtaining Funding
Executing The Plan
Acting As The Conductor
Putting Out Fires

## Slide 27: Role Of The Project Manager
Counseling And Facilitation
Encouraging The Team To Focus On Deadlines
Monitoring Progress By “Pounding The Pavement”
Evaluating Performance
Develop Contingency Plans
Briefing The Project Sponsor
Briefing The Team
Briefing The Customer
Closing Out The Project

## Slide 28: Role Of The Project Manager
https://www.youtube.com/watch?v=UBr3MM9_zd4

## Slide 29
Why is a Project Management System Necessary?

## Slide 30: Project Management
Time
Resources
Cost
Quality/Technology

## Slide 31: Benefits
Identification of functional responsibilities to ensure that all activities are accounted for, regardless of personnel turnover.
Minimizing the need for continuous improvement
Identification of time limits for scheduling
Identification of a methodology for trade-off analysis
Measurement of accomplishment against plans

## Slide 32: Benefits (continued)
Early identification of problems so that corrective action may follow
Improved estimating capability for future planning
Knowing when objectives cannot be met or will be exceeded

## Slide 33: Obstacles
Project complexity
Customer’s special requirements and scope changes
Organizational restructuring
Project risks
Changes in technology
Forward planning and pricing

## Slide 34: Humor
Project management is the art of creating the illusion that any outcome is the result of a series of predetermined, deliberate acts when, in fact, it was dumb luck.

## Slide 35: Resources
Money
Manpower
Equipment
Facilities
Materials
Information/technology

## Slide 36: Successful Culture
A good daily working relationship between the project manager and those line managers who directly assign resources to projects
The ability of functional employees to report vertically to their line manager at the same time they report horizontally to one or more project managers

## Slide 37: Interface Management
Managing human interrelationships within the project team
Managing human interrelationships between the project team and the functional organization
Managing human interrelationships between the project team and senior management
Managing human interrelationships between the project team and the customer’s organization, whether an internal or external organization

## Slide 38: Integration Management
Integrated Processes
Capital
Materials
Equipment
Facilities
Information
Personnel
Resources
Inputs
Integration Management
Products
Services
Profits
Outputs

## Slide 39: The Functional Role
The functional manager has the responsibility to define how the task will be done and where the task will be done (i.e., the technical criteria)
The functional manager has the responsibility to provide sufficient resources to accomplish the objective within the project’s constraints (i.e., who will get the job done).

## Slide 40: Functional Obstacles
Unlimited work requests (especially during competitive bidding)
Predetermined deadlines
All requests having a high priority
Limited number of resources
Limited availability of resources
Unscheduled changes in the project plan
Unpredicted lack of progress

## Slide 41: Functional Obstacles (continued)
Unpredicted lack of progress
Unplanned absence of resources
Unplanned breakdown of resources
Unplanned loss of resources
Unplanned turnover of personnel

## Slide 42: The Project Sponsor Interface
Project Team
Project Manager
Project Manager
Project Sponsor
Objective Setting
Up-Front Planning
Project Organization
Key Staffing
Master Plan
Policies
Monitoring Execution
Priority-Setting
Conflict Resolution
Executive-Client Contact
Relationship:
Project Sponsor: Lower/Middle Management
Project Sponsor: Senior Management
Priority Projects
Maintenance Projects

## Slide 43: Results of Good Planning
Assurance that functional units will understand their total responsibilities toward achieving project needs.
Assurance that problems resulting from scheduling and allocation of critical resources are known beforehand.
Early identification of problems that may jeopardize successful project completion so that effective corrective action and replanning can occur to prevent or resolve problems.

## Slide 44: Project Management in Non-Project-Driven Groups
Projects may be few and far between
Not all projects have the same project management requirements, and therefore they cannot be managed identically. This difficulty results from poor understanding of project management and a reluctance of companies to invest in proper training.
Executives do not have sufficient time to manage projects themselves, yet refuse to delegate authority.

## Slide 45: Project Management in Non-Project-Driven Groups (Continued)
Projects tend to be delayed because approvals most often follow the vertical chain of command. As a result, project work stays too long in functional departments.
Because project staffing is on a “local” basis, only a portion of the organization understands project management and sees the system in action.
There exists heavy dependence on subcontractors and outside agencies for project management expertise.

## Slide 46: High-level Reporting
The project manager is charged with getting results from the coordinated efforts of many functions. He should, therefore, report to the man who directs all those functions.
The project manager must have adequate organizational status to do his job effectively.
To get adequate and timely assistance in solving problems that inevitably appear in any important project, the project manager needs direct and specific access to an upper echelon of management

## Slide 47: High-level Reporting (continued)
The customer, particularly in a competitive environment, will be favorably impressed if his project manager reports to a high organizational echelon.

## Slide 48: Low-level Reporting
It is organizationally and operationally inefficient to have too many projects, especially small ones, diverting senior executives from more vital concerns.
Although giving a small project a high place in the organization may create the illusion of executive attention, its real result is to foster executive neglect o f the project.
Placing a junior project manager too high in the organization will alienate senior functional executives on whom he must rely for support.

## Slide 49
DELEGATION
OF AUTHORITY TO
PROJECT MANAGER
EXECUTIVE
MEDDLING
LACK OF UNDERSTANDING OF HOW PROJECT
MANAGEMENT SHOULD WORK
LACK OF TRAINING IN COMMUNICATIONS /
INTERPERSONAL SKILLS
THE TIP-OF-THE-ICEBERG SYNDROME
MANY OF THE PROBLEMS ASSOCIATED WITH PROJECT MANAGEMENT WILL
SURFACE MUCH LATER IN THE PROJECT AND RESULT IN MUCH HIGHER COSTS

## Slide 50: Chapter 2
Project management growth: concepts and definitions

## Slide 51: When to Use Project Management
Are the jobs complex?
Are there dynamic environmental considerations?
Are the constraints tight?
Are there several activities to be integrated?
Are there several functional boundaries to be crossed?

## Slide 52: The Need For Restructuring
Accomplish tasks that could not be effectively handled by the traditional structure
Accomplish onetime activities with minimum disruption to routine business

## Slide 53: Restructuring Problems
Project priorities and competition for talent may interrupt the stability of the organization and interfere with its long-range interests by upsetting the normal business of the functional organization.
Long-range planning may suffer as the company gets more involved in meeting schedules and fulfilling the requirements of temporary projects.

## Slide 54: Restructuring Problems (Continued)
Shifting people from project to project may disrupt the training of new employees and specialists. This may hinder their growth and development within their fields of specialization.

## Slide 55: Imperatives
The time span between project initiation and completion appears to be increasing.
The capital committed to the project prior to the use of the end item appears to be increasing.
As technology increases, the commitment of time and money appears to become inflexible.
Technology requires more and more specialized manpower.
The inevitable counterpart of specialization is organization.
The above five “imperatives” identify the necessity for more effective planning, scheduling, and control.

## Slide 56: Obstacles
Unstable economy
Shortages
Soaring costs
Increased complexity
Heightened competition
Technological changes
Societal Concerns

## Slide 57: Obstacles (Continued)
Consumerism
Ecology
Quality of work

## Slide 58: Results of NOT Controlling Obstacles
Decreased Profits
Increased manpower needs
Cost overruns, schedule delays, and penalty occurring earlier and earlier
An inability to cope with new technology
R&D results too late to benefit existing product lines
Temptation to make hasty decisions that prove to be costly

## Slide 59: Results of NOT Controlling Obstacles (Continued)
Management insisting on earlier and greater return on investment
Greater difficulty in establishing on-target objectives in real time
Problems in relating cost to technical performance and scheduling during the execution of the project

## Slide 60: Project Management Growth
Technology increasing at an astounding rate
More money invested in R&D
More information available
Shortening of project life cycles

## Slide 61: Early Reasons For Failure
There was no need for project management.
Employees were not informed about how project management should work.
Executives did not select the appropriate projects or project managers for the first few projects.
There was no attempt to explain the effect of the project management organizational structure on the wage and salary administration program.
Employees were not convinced that executives were in total support of the change (to project management).

## Slide 62: Advantages
Easy adaptation to an ever-changing environment
Ability to handle a multidisciplinary activity within a specified period of time
Horizontal as well as vertical work flow
Better orientation toward customer problems
Easier identification of activity responsibilities
A multidisciplinary decision-making process
Innovation in organizational design

## Slide 63: Project Management Evolution
Biblical Project Management
Military Project Management
Space Exploration
Heavy Construction
Other

## Slide 64: Life Cycle Phases for Project Management Maturity
Line Management Acceptance
Growth
Maturity
Embryonic
Executive Management Acceptance

## Slide 65: Life Cycle Phases for Level 2 Project Management Maturity
Executive Management Acceptance
Line Management Acceptance
Growth
Maturity
Embryonic
Recognize need
Recognize benefits
Recognize applications
Recognize what must be done

## Slide 66: Life Cycle Phases for Level 2 Project Management Maturity
Embryonic
Executive Management Acceptance
Line Management Acceptance
Growth
Maturity
Executive
Visible executive support
Executive understanding of project management
Project sponsorship
Willingness to change way of doing business
Management Acceptance

## Slide 67: Life Cycle Phases for Level 2 Project Management Maturity
Embryonic
Executive Management Acceptance
Growth
Maturity
Line Management Acceptance
Line management support
Line management commitment
Line management education
Willingness to release employees for project management training

## Slide 68: Life Cycle Phases for Level 2 Project Management Maturity
Embryonic
Executive Management Acceptance
Line Management Acceptance
Growth
Maturity
Growth
Development of a methodology
Use of life cycle phases
Commitment to planning
Minimization of “creeping scope”
Selection of a project tracking system

## Slide 69: Life Cycle Phases for Level 2 Project Management Maturity
Embryonic
Executive Management Acceptance
Line Management Acceptance
Growth
Maturity
Maturity
Development of a management cost/ schedule control system
Integrating cost and schedule control
Developing an educational program to enhance project management skills

## Slide 70: Driving Forces for Maturity
Capital projects
Customer expectations
Competitiveness
Executive understanding
New product development
Efficiency and effectiveness

## Slide 71: Benefits Of Project Mgt.
Project management will require more people and add to the overhead costs.
Profitability may decrease.
Project management allows us to accomplish more work in less time and with less people.
Profitability will increase.
Present View
Past View

## Slide 72: Benefits Of Project Mgt.
Project management will increase the amount of scope changes.
Project management creates organizational instability and increases conflicts.
Project management will provide better control of scope changes.
Project management makes the organization more efficient and effective.
Present View
Past View

## Slide 73: Benefits Of Project Mgt.
Project management is really “eye wash” for the customer’s benefit.
Project management will create problems.
Project management will allow us to work closer with our customers.
Project management provides a means for problem solving.
Present View
Past View

## Slide 74: Benefits Of Project Mgt.
Only large projects need project management.
Project management will increase quality problems.
All projects will benefit from project management.
Project management increases quality.
Present View
Past View

## Slide 75: Benefits Of Project Mgt.
Project management will create power and authority problems.
Project management focuses on suboptimization by looking at only the project.
Project management will reduce the majority of the power struggles.
Project management allows people to make good company decisions.
Present View
Past View

## Slide 76: Benefits Of Project Mgt.
Project management delivers products to a customer.
The cost of project management may make us noncompetitive.
Project management delivers solutions to a customer.
Project management will increase our business.
Present View
Past View

## Slide 77: Industry Classification (By Project Management Utilization)
Project -Driven
PM has P&L responsibility
PM is a recognized profession
Multiple career paths
Income comes from projects
Hybrid
Production driven but with many projects
Emphasis on new product develop.
Short product life cycles
Marketing-orient.
Need for rapid develop. process
a
Program Management
Very few projects
Profitability from production
Large brick walls
Long life cycle products
Product Management
Present
Past
Project Management
Non-
Project-Driven

## Slide 78: From Hybrid to Project-Driven
Entrance via project-driven divisions such as MIS and R&D
Entrance via marketing, sales, engineering and R&D
Traditional Project
Management
Modern Project
Management
1960 -1990 Hybrid
1990 -Present Hybrid

## Slide 79: New Processes Supporting Project Management
1960- 1985
1985
1990
1991- 1992
1993
1994
No Allies
Total Quality Manage- ment
Concurrent Engineer- ing
Empower- ment and Self- Directed Teams
Re- Engineering
Life Cycle Costing
Increasing Support

## Slide 80: New Processes Supporting Project Management (Continued)
1995
1996
1997-
1998
1999
2000
Scope
Change
Control
Risk
Management
Project
Offices
And
COEs
Co- Located
Teams
Multi-
National
Teams
Increasing Support

## Slide 81: New Processes Supporting Project Management (Continued)
2001
2002
2003
2004
2005
Maturity
Models
Strategic
Planning
For
Project
Management
Intranet
Status
Reports
Capacity
Planning
Models
Six Sigma Project Mgt
Increasing Support

## Slide 82: New Processes Supporting Project Management (Continued)
2006
2007
2008
2009
Virtual Project Teams
Lean
Project Teams
Best
Practice
Libraries
Capacity
Planning
Models
Increasing Support

## Slide 83: Definition of a Project Life Cycle
Resources
Utilized
RESOURCES
TIME
CONCEPTUAL
PHASE
DETAILED PLANNING PHASE
FEASIBILITY AND
PRELIMINARY PLANNING PHASE
IMPLEMENTATION
PHASE
CONVERSION
OR TERMINATION PHASE
PMO
PMO *

## Slide 84
The Definition Of Success

## Slide 85: Success
Definition of Success
  Primary Factors
    Within Time
    Within Cost
    Within Quality
    Accepted by The Customer

## Slide 86: Success
  Secondary Factors:
    Customer Reference
    Follow-on Work
    Financial Success
    Technical Superiority
    Strategic Alignment
    Regulatory Agency Relations
    Health and Safety
    Environmental Protection
    Corporate Reputation
    Employee Alignment
    Ethical conduct

## Slide 87: Key Performance Indicators
These are shared learning topics which allow us to maximize what we do right and correct what we do wrong.

## Slide 88: Risk Planning
Poor Risk Management
Technical Inability
Customer Expectations
Actual Performance
Performance
Time

## Slide 89: The starting point in the development of any project management methodology is the implementation of a stage-gate process.

## Slide 90: Stages
Groups of series or parallel activities (based upon the risks of the project)
Managed by cross-functional teams
To reach a predetermined deliverable established by management

## Slide 91: Gates
Structured decision points at the end of each stage
Number of gates must be limited

## Slide 92: Gatekeepers
Individuals (i.e. sponsors) or groups of individuals assigned by senior management
Empowered to enforce the structured process (including change management)
Authorized to evaluate performance and make decisions
And willing to provide the team necessary technical and business information

## Slide 93: Gatekeeper’s decisions
Proceed to next gate with the original objectives
Proceed to the next gate with revised objectives
Delay making a gate decision until further information is obtained
Terminate the project

## Slide 94: Stage-Gate Failures
Assigning gatekeepers and not empowering them to make decisions
Assigning gatekeepers who are afraid to terminate a project
Failure to provide the team with information critical to gate reviews
Allowing the team to focus more on the gates than on the stages

## Slide 95: Methodology Inputs
Project Management Methodology
Organization
Work (Tasks)
Tools
People

## Slide 96: Resistance to Change
Low
Neutral
High
Finance
H.R.
Eng.
I.T.
Sales
Marketing
Procurement
Manu.
R&D

## Slide 97: Change Process
Support for Change
Time
Denial
Resistance
Exploration
Resistance
Support

## Slide 98: Multi-project Management
Are the project objectives the same?
  For the good of the project?
  For the good of the company?
Is there a distinction between large and small projects?
How do we handle conflicting priorities?
  Critical versus critical projects
  Critical versus non-critical projects
  Non-critical versus non-critical projects

## Slide 99: Prepare for Next Week
Read Chapter 3: Organizational Structures
Read Chapter 4: Organizing and Staffing the Project Office and Team
Read Chapter 5: Management Functions
Take Quiz #1 by Wednesday (1/11) at 5:30pm
Online students: Post to Discussion board for week #1 by 1/11 at 5:30pm